Practical No: 9

Practical 9: Estimate the approximate size, effort, development time and cost for your decided system.

1. Software Size Estimation:
Selected Method: Function Point Analysis (FPA)

Function Point Analysis is appropriate because the E-Commerce Website's size can be estimated from its user-visible functionality without depending on a particular programming language or technology.

The estimate is based on the established project scope, including customer management, products, search/filtering, cart, checkout/payment, orders, recommendations, inventory, discounts and administration.

Function Point Calculation
Using standard average-complexity weights:

| Function Type | No. | Weight | Contribution |
| --- | --- | --- | --- |
| External Inputs (EI) | 7 | 4 | 28 |
| External Outputs (EO) | 2 | 5 | 10 |
| External Inquiries (EQ) | 3 | 4 | 12 |
| Internal Logical Files (ILF) | 3 | 10 | 30 |
| External Interface Files (EIF) | 1 | 7 | 7 |
| Unadjusted Function Points (UFP) |  |  | 87 |

1. Function Point Estimation:

Formula:

UFP = Σ (Number of Functions × Weight)

UFP = 28 + 10 + 12 + 30 + 7

UFP = 87

For this academic estimate, assume Value Adjustment Factor (VAF) = 1.00, since detailed adjustment-factor ratings are not available.

FP = UFP × VAF

FP = 87 × 1.00

FP = 87

Approximate Software Size:

87 Function Points

2. Effort Estimation:

For a small academic project, assume a productivity of:

Productivity = 12 FP / Person-Month

Formula:

Effort = Function Points / Productivity

Substitution:

Effort = 87 / 12

Effort = 7.25 Person-Months

Final Effort:

7.25 Person-Months

3. Development Time Estimation:

The project has 3 team members.

Formula:

Development Time = Effort / Team Size

Substitution:

Development Time = 7.25 / 3

Development Time = 2.42 Months

Therefore:

Development Time = 2.42 Months

This is approximately 10–11 weeks, which is consistent with the semester mini-project timeline planned in Practical-8.

4. COST ESTIMATION

Assume an academic development cost of:

₹25,000 per Person-Month

Formula:

Development Cost = Effort × Cost per Person-Month

Substitution:

Development Cost = 7.25 × ₹25,000

Development Cost = ₹181,250

Final Approximate Development Cost:

₹1,81,250

The ₹25,000/person-month figure is an academic estimation assumption, not an actual commercial salary or project quotation.

Conclusion:
The approximate size, effort, development time and cost of the E-Commerce Website have been estimated using Function Point Analysis and an academic productivity/cost assumption. The estimated development effort is 7.25 Person-Months, requiring approximately 2.42 months for a 3-member team, with an estimated cost of ₹1,81,250.